## Template
Program Communications Plan Program: IPIP Date and Version: 1 April 20XX
Communications Item | Item Owner | Target Audience | Media/Channels | Frequency | Purpose/Objective | Comments
Program Kickoff Meeting | Raj Patel | Executive Sponsor, Program Manager, Project Leads, Department Heads | Virtual meeting (Zoom/In-person) | One-time (Program Start) | Introduce program vision, scope, key roles, timeline, and expectations | Meeting recording and minutes circulated afterward; Q&A to clarify roles and milestones
Weekly/Bi-Weekly Status Emails | Program Manager | All internal stakeholders (Project Team, Sponsors, Department Heads) | Email | Weekly or bi-weekly | Provide brief status updates on progress, highlight accomplishments, flag issues, and share upcoming milestones | Recipients can respond with queries/suggestions; include dashboards/visual metrics as attachments
Monthly Steering Committee Meetings | Raj Patel | Executive Sponsor, Senior Department Heads, Program Manager, Project Leads | In-person & Virtual (Hybrid) | Monthly | Review overall program progress, assess risk management, strategic alignment, and make key decisions | Follow-up email includes action items; minutes documented and shared with all committee members
Bi-Monthly Detailed Progress Reports | Program Manager | Executive Sponsor, Program Manager, Project Leads | PDF Report via Email or Shared Dashboard | Every 2 months | Provide comprehensive updates on KPI metrics, project progress, issues encountered, and next steps | Includes detailed financial, timeline, and quality metrics; structured with visuals and graphs; feedback integrated via follow-up discussions
Training & Workshop Sessions | Training Lead | HR staff, IT teams, Sales/CRM teams | In-person sessions and/or Webinars | Monthly or as needed | Equip teams with necessary tools and skills to utilize AI, cloud, and CRM systems effectively; address adoption issues | Pre-session agenda circulated; post-session surveys to capture feedback and measure training effectiveness
Stakeholder Feedback Sessions | Change Management | Key end-users, Department Heads, Change Management Team | Focus Group Meetings, Surveys | Quarterly | Gather qualitative feedback, address concerns, and identify opportunities for process improvement | Summarize feedback and circulate improvement action plans; session findings integrated into subsequent project reviews
Ad-hoc Issue Escalation Meetings | Raj Patel/Project Leads | Relevant team members, subject matter experts | Phone/Video call or In-person | As needed | Address urgent issues or risks not covered in regular meetings | Real-time escalation; documented with immediate resolution action items
Post-Implementation Review & Closure Meeting | Raj Patel | All stakeholders, Executive Sponsor, Program Manager, Project Leads | In-person or Virtual Workshop | Once, at program close | Evaluate overall program performance, lessons learned, and establish recommendations for future programs | Formal review meeting with a final report; documented lessons learned and transition recommendations to ongoing operations