## Risk Register Template
Program Risk Register Program: Date and Version: IPIP 1 April 20XX
Risk # | Program Component | Cause | Event | Impact | Category | Risk Owner | Probabilty | Impact | Risk Score | Trigger | Response
R-001 | Delayed Adoption of AI Tools | Insufficient training and resistance from HR staff | Insufficient training and resistance from HR staff | Delays in achieving recruitment workflow optimization and slower realization of benefits |  | HR Director (David Lee) | 4 | 4 | 16 |  | Develop and implement a phased AI training program; appoint early adopters as champions; schedule refresher sessions
R-002 | Cloud System Performance Issues | Inadequate performance testing; vendor delays | Inadequate performance testing; vendor delays | Increased downtime, reduced system scalability and overall operational efficiency |  | IT Director (Sandra Patel) | 3 | 4 | 12 |  | Allocate additional resources for thorough performance testing; set up real-time monitoring; engage vendors early for proactive support
R-003 | Integration Challenges Between CRM & Legacy Systems | Complex legacy systems causing integration bottlenecks | Complex legacy systems causing integration bottlenecks | Delayed CRM automation rollout; potential reduction in customer satisfaction improvements |  | Sales Director (Michael Brown) | 4 | 3 | 12 |  | Deploy dedicated integration specialists; conduct early-stage integration testing; plan for iterative troubleshooting; schedule contingency time in the project plan
R-004 | Budget Overruns | Unplanned expenses (e.g., vendor delays, additional resource needs) | Unplanned expenses (e.g., vendor delays, additional resource needs) | Potential scope reductions, delays, and strain on overall program financials |  | Program Manager (Raj Patel) | 3 | 5 | 15 |  | Establish strict financial controls and contingency funds; conduct periodic budget reviews; communicate closely with vendors to anticipate additional costs
R-005 | Employee Resistance to Process Changes | Lack of engagement and reluctance to adopt new processes | Lack of engagement and reluctance to adopt new processes | Slow down in process improvement and longer adaptation period; potential reduction in efficiency gains |  | Change Management Specialist | 4 | 3 | 12 |  | Implement robust change management; conduct regular engagement sessions and feedback surveys; offer incentives and continuous support during and after transitions
R-006 | Opportunity Risk: Early AI Adoption (Opportunity) | Early successful training and rapid adoption by early users | Early successful training and rapid adoption by early users | Accelerated benefit realization can cause resource imbalance if not managed appropriately |  | HR Director (David Lee) | 3 | 4 | 12 |  | Leverage early successes to scale training efforts; monitor resource allocation closely; adjust rollout plan to balance resource use across projects
Total Risk Score | [8 empty] | 79
Explanation of Columns: Risk #: Unique identifier for the risk. Program Component: The part of the program affected by the risk. Cause: The root cause or condition driving the risk. Event: Description of the risk event. Impact: The consequence or impact of the risk event. Category: The type or category of the risk (e.g., Schedule, Technical, Operational, Legal, Financial). Risk Owner: The person responsible for managing the risk. Probability: The likelihood of the risk occurring (1-5). Impact: The severity of the risk's impact (1-5). Threats are scored as a positive number. Opportunities are scored as a negative number. Risk Score: A score representing the combined effect of probability and impact. Trigger: The indicator or event that signifies the risk is occurring. Response: The planned action to mitigate or capitalize on the risk. Total Risk Score: The sum of all risk scores. Threats increase the total risk score. Opportunities reduce the overall risk score.