## Solution
Program Communications Plan Program: TechVision Corporate Digital Transformation Program Date and Version: 1 Jun 20xx, Version 1
Communications Item | Item Owner | Target Audience | Media/Channels | Frequency | Purpose/Objective | Comments
Program Kickoff Meeting | Program Manager | All Stakeholders | Virtual Meeting (Zoom) | Once (at the start) | Introduce the program, set expectations, and align on goals. | Ensure full attendance; record session for those unable to attend.
Weekly Progress Report | Project Managers | Program Steering Committee, Executive Sponsor | Email, PM Tool | Weekly | Provide status updates on project progress, issues, and upcoming tasks. | Use project management software for tracking.
Monthly Steering Committee Meeting | Program Manager | Steering Committee | In-person/Virtual Meeting | Monthly | Review program progress, address risks, and make strategic decisions. | Prepare agenda in advance and provide reports 2 days before.
Milestone Reviews | Project Managers | Executive Sponsor, Program Steering Committee | Presentation, Email | End of each milestone | Validate achievement of key milestones, identify lessons learned. | Align these with the program's major phases.
Stakeholder Feedback Survey | HR Director | Employees | Online Survey (Google Forms) | Quarterly | Collect feedback on new HR systems, training, and ease of use. | Use data to improve training and system interface.
Customer Engagement Update | Sales Director | Customers | Email Newsletter | Bi-Monthly | Inform customers about upcoming CRM features and improvements. | Include a customer service contact for questions.
Security Awareness Training | IT Director | All Employees | E-Learning, Email | As needed (upon new launches) | Ensure employees understand the new cybersecurity systems and protocols. | Follow up with a quiz to test understanding.
Change Management Workshops | Change Management Specialist | Employees | Workshops (In-person/Virtual) | During Major Phases | Equip employees with knowledge and skills for adapting to new systems. | Tailor content to departments.
Executive Sponsor Briefings | Program Manager | Executive Sponsor | Virtual/Phone Call | Bi-Weekly | Provide high-level program updates and discuss escalated issues. | Keep the briefings concise and focused on critical updates.
Risk and Issue Logs | Program Manager | Project Teams, Steering Committee | PM Software | Continuous | Document and track program risks and issues for timely resolution. | Regularly updated and reviewed during meetings.
End-of-Phase Reviews | Program Manager | All Stakeholders | Email, PM Tool, Meeting | End of each phase | Summarize phase completion, success metrics, and any blockers. | Engage all project managers for comprehensive reporting.