## Risk Register Template
Program Risk Register Program: Date and Version:
Risk # | Program Component | Cause | Event | Impact | Category | Risk Owner | Probabilty | Impact | Risk Score | Trigger | Response
Provide comprehensive training and hire an external AI consultant for initial phases.
Conduct security audits, involve third-party experts, implement real-time monitoring tools during migration.
Assign a dedicated integration specialist, conduct multiple testing phases.
Implement a hybrid security model combining AI and manual detection, enhance AI system training.
Develop targeted change management strategies, offer support and incentives, adjust training content based on feedback.
Establish strict budget controls, conduct regular financial reviews, allocate contingency funds.
Establish SLAs, maintain regular communication, have backup providers ready.
Perform comprehensive backups, conduct pre-migration testing, verify data integrity post-migration.
Negotiate with vendors for discounts, streamline resource usage to ensure efficient cost management.
Maximize automation for HR tasks, reallocate saved time and resources to strategic HR initiatives.
Total Risk Score | [8 empty] | 0
Explanation of Columns: Risk #: Unique identifier for the risk. Program Component: The part of the program affected by the risk. Cause: The root cause or condition driving the risk. Event: Description of the risk event. Impact: The consequence or impact of the risk event. Category: The type or category of the risk (e.g., Schedule, Technical, Operational, Legal, Financial). Risk Owner: The person responsible for managing the risk. Probability: The likelihood of the risk occurring (1-5). Impact: The severity of the risk's impact (1-5). Threats are scored as a positive number. Opportunities are scored as a negative number. Risk Score: A score representing the combined effect of probability and impact. Trigger: The indicator or event that signifies the risk is occurring. Response: The planned action to mitigate or capitalize on the risk. Total Risk Score: The sum of all risk scores. Threats increase the total risk score. Opportunities reduce the overall risk score.