## Template
Program Stakeholder Register Program: Corporate Digital Transformation Date and Version: 1 Jun 20xx Version 1
Position | Name | Organization | Component Supported | Role Description | R: Responsible | A: Accountable | C: Consulted | I:Informed | Required Timeframe | Comments
utive Sponsor | Emily Zhang | TechVision Corporation | Entire Program | Provide strategic direction and approval for the program. | X | X | X |  | Ongoing | Key decision-maker for the program.
Program Manager | Priya Simpson | TechVision Corporation | Entire Program | Oversee and manage the execution of the program. |  | X | X | X | Ongoing | Key program manager.
HR Director | David Lee | TechVision Corporation | AI-Powered HR Management | Lead the implementation of AI-powered HR management. | X |  |  | X | Months 3-6 | Crucial for successful HR system transformation.
IT Director | Sandra Patel | TechVision Corporation | Cloud Migration, Cybersecurity Enhancement | Lead the implementation of cloud migration and cybersecurity measures. | X |  |  | X | Months 4-12 | Crucial for cloud and cybersecurity project success.
Sales Director | Michael Brown | TechVision Corporation | CRM System Development | Lead the development of the CRM system. | X |  |  | X | Months 6-10 | Critical for CRM system success.
Customer Service Director | Linda Nguyen | TechVision Corporation | CRM System Development | Support the CRM system development and customer engagement. |  |  | X | X | Months 6-10 | Key to customer-facing aspects of the CRM system.
Employees | All Staff | TechVision Corporation | All Projects | Adopt and adapt to new systems and processes. |  |  |  | X | Ongoing | Must be fully onboard with new systems.
Customers | Various | TechVision Corporation | CRM System Development | Provide feedback and engage with new CRM system. |  |  | X | X | Ongoing | Key to the success of customer engagement initiatives.
RACI Terms Defined | ROLE | DEFINED
| R | Responsible for performing work or tasks
| A | Accountable for outcomes
| C | Consult as a Subject Matter Expert (SME)
| I | Inform as project progresses