## Template
Program Stakeholder Register Program: Date and version:
Position | Name | Organization | Component Supported | Role Description | R: Responsible | A: Accountable | C: Consulted | I: Informed | Required Timeframe | Comments
RACI terms defined | ROLE | DEFINED
| R | Responsible for performing work or tasks
| A | Accountable for outcomes
| C | Consult as a subject matter expert (SME)
| I | Inform as project progresses

## Example
Program Stakeholder Register Program: AI-Driven Personalization and Customer Engagement Date and version: 10 Oct 20xx, version 1
Position | Name | Organization | Component Supported | Role Description | R: Responsible | A: Accountable | C: Consulted | I: Informed | Required Timeframe | Comments
Program Manager | Alice Johnson | HealthTech Hub | Entire Program | Oversees the entire program execution | X | X | X | X | Ongoing | Primary stakeholder managing overall delivery
AI Product Lead | David Lee | HealthTech Hub | AI-Powered Product Recommendation Engine | Leads the development and integration of AI products | X | X | X | X | Phase 1 | Critical for AI development, works closely with IT and customer experience
Customer Experience Manager | Sophia Martinez | HealthTech Hub | Personalized Health Content Delivery | Ensures customer engagement and satisfaction | X |  | X | X | Phase 2 | Drives customer satisfaction through personalized content
IT Infrastructure Manager | John Carter | HealthTech Hub | AI Chatbot for Customer Support | Manages the IT infrastructure for AI implementation | X |  |  | X | Phase 2 | Ensures technical infrastructure supports AI initiatives
Data Privacy Officer | Priya Patel | HealthTech Hub | All AI Components | Ensures compliance with data privacy regulations | X | X | X | X | Ongoing | Key to compliance and risk management
Marketing Lead | Emma Thompson | HealthTech Hub | AI-Powered Product Recommendation Engine | Oversees marketing and customer outreach | X |  | X | X | Phases 1 & 2 | Coordinates marketing with AI insights
Customer Support Lead | Michael Richards | HealthTech Hub | AI Chatbot for Customer Support | Leads customer support initiatives | X |  | X | X | Phase 2 | Supports customers with AI-driven tools
External AI Consultant | Consultant Agency XYZ | Consultant Agency | All AI Components | Provides external expertise on AI implementation | X | X | X | X | Phases 1 - 3 | Brings in AI expertise, especially for initial setup
RACI terms defined | ROLE | DEFINED
| R | Responsible for performing work or tasks
| A | Accountable for outcomes
| C | Consult as a subject matter expert (SME)
| I | Inform as project progresses